## Slide 1: Software Project Management (SPM) Unit- V
Prepared by: Neha Tripathi

## Slide 2: SPM
Risk Management

## Slide 3: Basics
Risk
- “Risk is a problem that may cause some loss or threaten the success of the project, but which has not happened yet”.
- Risk is an input , event or circumstances that hampers or act as an obstacle to the successful completion of the project.
Risk Management
- Risk management is the process of identifying addressing and eliminating these problems before they can damage the project.
Risk management is the area which tries to ensure that the impact of risks on cost, quality and schedule is minimized.
The main purpose of risk management is to identify and manage the risks associated with a software project and solve the problem.

## Slide 4: Risk Management Activities
Risk Identification
Risk Assessment
Risk Abatement/Containment
- Risk Avoidance
- Risk Transfer
- Risk Reduction

## Slide 5: Risk Identification
A software project can be affected by a large variety of risks.
In order to be able to systematically identify the important risks which might affect a software project, it is necessary to categorize risks into different classes.
The project manager can then examine which risks from each class are relevant to the project.
There are three main categories of risks which can affect a software project:
- Project risks
- Technical risks
- Business risks

## Slide 6: Continue….
Project risks
Project risks concern varies forms of budgetary, schedule, personnel, resource, and customer-related problems.
Technical risks
Technical risks concern potential design, implementation, interfacing, testing, and maintenance problems. Technical risks also include ambiguous specification, incomplete specification, changing specification, technical uncertainty, and technical obsolescence.
Business risks.
This type of risks include risks of building an excellent product that no one wants, losing budgetary or personnel commitments, etc.

## Slide 7: Risk Assessment
The objective of risk assessment is to rank the risks in terms of their damage causing potential.
For risk assessment, first each risk should be rated in two ways:
- The likelihood of a risk coming true (r).
- The consequence/impact of the problems associated with that risk (s).
Based on these two factors, the priority (p) of each risk can be computed:
p = r * s
Where, p is the priority with which the risk must be handled,
r is the probability of the risk becoming true, and
s is the severity of damage caused due to the risk becoming true.
If all identified risks are prioritized, then the most likely and damaging risks can be handled first and more comprehensive risk abatement procedures can be designed for these risks.

## Slide 8: Risk Containment/Abatement
After all the identified risks of a project are assessed, plans must be made to contain the most damaging and the most likely risks.
Different risks require different containment procedures..
There are three main strategies to plan for risk containment:
- Avoid the risk:
This may take several forms such as discussing with the customer to change the requirements to reduce the scope of the work, giving incentives to the engineers to avoid the risk of manpower turnover, etc.
- Transfer the risk:
This strategy involves getting the risky component developed by a third party, buying insurance cover, etc.
- Risk reduction:
This involves planning ways to contain the damage due to a risk. For example, if there is risk that some key personnel might leave, new recruitment may be planned.

## Slide 9: Risk leverage
To choose between the different strategies of handling a risk, the project manager must consider the cost of handling the risk and the corresponding reduction of risk.
For this the risk leverage of the different risks can be computed.
Risk leverage is the difference in risk exposure divided by the cost of reducing the risk.
More formally,
risk leverage = (risk exposure before reduction – risk exposure after reduction) / (cost of reduction)